## Lexington MS4 Activity Calendar
Column1 | MS4 Task | Priority | Start Date | End Date | Responsibility | Completed | Notes | Column9 | Predecessors | Duration
| MCM 1: Public Education & Outreach | [8 empty] | 9d
| BMP 1: Develop brochures regarding stormwater issues and methods to prevent contamination. |  | 2016-08-08 | 2016-11-29 | [5 empty] | 9d
| Distribute existing NE H20 PEO Materials: Obtain from Leann Sato |  |  |  | Nick H. |  |  |  |  | 9d
| Update and redistribute existing Lexington-specific materials where possible. |  |  |  | Nick H. |  | Storm Drain Stenciling, Weed ordinance Flyer (bi-lingual), door hangings |  |  | 4d
| Evaluate and update Public Education & Outreach Strategy for remainder of 2016. |  |  |  | Nick H., Bill Brecks.
| BMP 2: Stomwater Program Website Updating |  | 2016-08-12 | 2016-09-01 | [5 empty] | 9d
| Organize and Update Lexington Website Page |  |  |  | Nick H., Bill Brecks, Webmaster |  | Include links to local references, ordinances. Include stormwater-related materials created by NE H20. Include phone number for concerns, complaints. Include PEO work done (presentations, event images). Include helpful links |  |  | 9d
| Link to NE H20 Website |  |  |  | Webmaster |  | Link to the NE H20 Website from the Lexington stormwater page. Take credit in Annual reporting. |  |  | 2d
| BMP 3: Cooperate with local community organizations, such as the Chamber of Commerce, local civic organizations, and other groups to provide education regarding stormwater issues. |  | 2016-09-01 | 2016-09-12 | [5 empty] | 21d
| Compile previous information on organization or participation in community activities. |  |  |  | Nick H. |  | Look through archives for Run/Walk 5K's, Pond cleanup near high school with school clubs/teams, Any others?? |  |  | 2d
| Determine events & frequencies on an annual basis. |  |  |  | Nick H., Bill Brecks |  | Establish if any participation can be done in remainder of 2016 based on events calendar. |  |  | 3d
| Determine assessment for requests for activity participation or sponsorship |  |  |  | Nick H., Bill Brecks |  | If someone asks for help/donation, assess the public benefit for stormwater awareness to determine whether you say yes or no. |  |  | 3d
| BMP 4: Develop Public Service Announcements |  | 2016-08-08 | 2016-08-26
| Utilize NE H20 Materials: Obtain from Leann Sato |  |  |  | Nick H. |  | Take credit for media campaigns already in process. Utilize local media (print, newsletters, website). Utilize Social Media (Twitter, Facebook) |  |  | 4d
| Include Public Service/Stormwater Article in next newspaper or Newsletter opportunity. |  |  |  | Nick H.
MCM 2: Public Involvement
| BMP 1: Develop Call-In System for public to access educational information related to stormwater |  | 2016-08-15 | 2016-08-18 | [5 empty] | 4d
| Utilize same hotline number for complaints. Ensure current number is still accurate. |  |  |  | Bill Brecks |  |  |  |  | 4d
| Create email inquiry system for public to obtain more information (Form page on website) |  |  |  | Nick H., Bill Brecks, Webmaster |  |  |  |  | 4d
| BMP 2: Update existing City website to include information on stormwater, with links to other useful sites |  | 2016-08-12 | 2016-09-01 |  |  | See MCM 1, BMP 2
| BMP 3: Organize & hold public meetings and attend meetings with affected groups (i.e. homebuilders association, etc) to discuss stormwater program and solicit feedback |  | 2016-08-08 | 2016-08-11 |  |  | Schedule ,Organize & hold meetings a minimum of once per year. Compile summary of meetings and feedback received at each meeting. |  |  | 4d
| BMP 4: Sponsor a community-wide cleanup Day and encourage individual and group participation. Emphasize contaminants contributing to the impairment of the Platte River. |  | 2016-11-01 | 2016-11-30 | Nick H., Bill Brecks, Department Heads |  | Schedule day for 2017. Begin preparations.
Research online for clean-up days from other similar sized small communities.
Schedule Community-Wide Clean-up day for 2017
| Compile list of local groups to encourage participation from, Include in PEO Strategy document. | [5 empty] | Boy Scouts, Girl Scouts, Kiwanis, Lexington Community schools/school clubs, corporate participants, etc.
MCM 3: Illicit Discharge Detection & Elimination (IDDE)
| BMP 1: Develop Standard Operating Procedures for Program |  | 2016-09-01 | 2016-09-30 | Nick H., Bill Brecks |  |  |  |  | 105d
Review ordinance and previous files for progress
Discuss creation of an IDDE Program document incorporating all policies and procedures for the program.
Draft IDDE Program Document
Adopt final IDDE Program Document
| BMP 2: Storm Sewer System mapping |  | 2016-09-01 | 2016-12-31
| Review System maps Annually for accuracy. |  |  |  | Bill Brecks |  | Ongoing task.
| Regularly update map with new areas as the come online. |  |  |  | Bill Brecks |  | Ongoing task.
Adopt final IDDE Program Document
| BMP 3: Perform Dry Weather Inspections for Outfalls |  | 2016-09-01 | 2016-10-31
| Develop Standard Operating Procedures for Dry Weather Inspections |  |  |  | Bill Brecks, Nick H.
| Establish Inspection frequency for Outfalls |  |  |  | Bill Brecks, Nick H.
| Utilize a database tracking system |  |  |  | Bill Brecks, Nick H. |  | ASIST Tracking System, GIS, Google Earth KMZ locations, are all possible tools to use
| Conduct Dry Weather Inspections for all known outfalls 30" diameter & larger |  |  |  | Nick H., City Staff
| BMP 4: Storm Drain Stenciling |  | 2016-08-08 | 2016-12-30 | [5 empty] | 105d
| Ensure all new stormdrains include either stencil or stamp. |  |  |  | Nick H. |  |  |  |  | 105d
| Track number of installed stencils/stickers for calendar year |  |  |  | Nick H. |  | Include in Annual Report |  |  | 105d
| Develop Standard Operating Procedure for storm drain stenciling |  |  |  | Nick H. |  | SOP should include procedures for both new and existing storm drains |  |  | 21d
| BMP 5: Use PEO Materials to educate public about illegal dumping and illicit discharges. |  | 2016-10-01 | 2016-10-31
Research EPA Website and other MS4 sources for existing materials to link to via website.
Research print materials available through NE H20 (Call Leann Sato)
MCM 4: Construction Stormwater Management
| BMP 1: Develop an Erosion & Sediment Control Ordinance |  | 2016-09-01 | 2016-10-31
| Review current ESC Ordinance against current MS4 General Permit and Construction Stormwater General Permit for completeness and accuracy. |  |  |  | Nick H., Bill Brecks |  |  |  |  | 22d
| Draft Ordinance update for any inclusions needed, based on review. |  |  |  | Nick H., Bill Brecks |  |  |  |  | 22d
| BMP 2: Develop or Adopt Design Standards for Stormwater Runoff Control Measures |  |  |  |  | 0.67 | Original SWMP language. The intent was for NE H20 to create their own design manual. This never materialized. This language will go away in subsequent SWMP updates
| Ensure design guidance is given in ESC Ordinance |  |  |  | Nick H. | 100% | No City standards and specifications for Erosion & Sediment Controls. Refers to NDOR stds, specs & Guidance. Any other alternative methodology approved by the city. |  |  | 18d
| Ensure approved design guides are linked on Stormwater Website |  |  |  | Nick H., Webmaster |  | Include links to NDOR Standards & specs. |  |  | 9d
| BMP 3: Site Inspection and Plan Review Program |  | 2016-08-08 | 2016-10-31
| Review current files for previously proposed procedures/SOP's for Inspection and plan review |  |  |  | Nick H., Bill Brecks |  |  |  |  | 18d
| Track the number of site inspections conducted annually |  |  |  | Nick H. |  | Ongoing Task |  |  | 105d
| Track the number of ESC Plan reviews conducted annually. |  |  |  | Nick H., Bill Brecks |  | Ongoing task |  |  | 105d
| Draft procedures/SOP updates, or formally adopt previously proposed SOP's as policy. |  |  |  | Nick H., Bill Brecks |  |  |  |  | 22d
| Establish inspection frequency for all active construction sites over one acre in disturbance |  |  |  | Nick H. |  |  |  |  | 5d
| Establish procedures for enforcement of construction stormwater ordinance (Enforcement Response Plan) |  |  |  | Nick H., Bill Brecks |  | Draft Enforcement Response Plan Created for NE H20. |  |  | 43d
| BMP 4: Educate Contractors and the Development Community |  | 2016-12-01 | 2016-12-30
| Schedule Annual ESC Education Program Presentation |  | 2016-12-01 | 2016-12-30 |  |  | Best held in Late Winter, prior to active construction season. |  |  | 22d
| Develop Materials to educate developers, contractors and sub-contractors |  |  |  | Nick H., Bill Brecks
| Coordinate with local/state homebuilder's association for cooperation and buy-in. |  |  |  | Nick H., Bill Brecks |  | Nebraska State Homebuilder's Association
MCM 5: Post-Construction Stormwater Management
| BMP 1: Develop a Post-Construction Stormwater Ordinance | [5 empty] | Saved for 2017
| Review Proposed Timeline/Schedule for Orrdinance adoption established by NE H20 recommendations (Fall 2015) |  | 2016-10-01 | 2016-10-31 | Nick H., Bill Brecks |  |  |  |  | 18d
| Establish Target Adoption Date for Post-Construction Stormwater Program Ordinance |  | 2016-10-01 | 2016-10-31 | Nick H., Bill Brecks |  |  |  |  | 22d
| Establish public involvement schedule for Post-Construction Program based on Ordinance Adoption Target date. |  | 2016-10-01 | 2016-10-31 | Nick H., Bill Brecks |  |  |  |  | 22d
| Establish public process strategy for Post Construction Program. |  | 2016-10-01 | 2016-10-31 | Nick H., Bill Brecks |  | Utilize information gathered from NE H20 Meetings on this subject, as well as other recent public process examples (i.e. Lincoln, Kearney). Establish goals, objectives, key stakeholders, subject matter to discuss (when, how). Agree on what a positive outcome looks like, why this is being done, and an agressive "how-to" based on those answers. |  |  | 22d
| BMP 2: Develop Post-Construction Stormwater Treatment BMP Inspection and Plan Review SOP's | [5 empty] | Saved for 2017
| Participate in NE H20 coordination meetings to establish these SOP's collectively. |  |  |  | Nick H., Bill Brecks |  | Saved for 2017
BMP 3: Develop Educational materials for the Development community
| Participate in NE H20 coordination meetings to establish many of these educational materials collectively. |  |  |  | Nick H., Bill Brecks |  | Saved for 2017
MCM 6: Good Housekeeping & Pollution Prevention
| BMP 1: Evaluate Municipal Operations & minimuze pollutant exposure to stormwater runoff |  | 2016-08-12 | 2016-09-30
| Collect an inventory of all municipal facilities |  |  |  | Nick H. , Bill Brecks |  | Street address, facility contact, facility use. |  |  | 21d
| Finalize and Implement Facility Runoff Control Plan (FRCP) for City Service Building. |  |  |  | Nick H. Bill Brecks, Facility Manager |  | Would include site-specific training component for facility staff, walk-through inspection training for select staff, monthly inspections by staff. |  |  | 21d
| Perform "Hot Spot" rapid assessment of each Municipal facility/property for pollutant risk. |  |  |  | Nick H., Bill Brecks, |  | Inherent pollutant risck factors may suggest a Facility Runoff Control Plan is needed at a facility. A draft FRCP was created for the Main Public Works facility.
| BMP 2: General Stormwater Good Housekeeping & Pollution Prevention Training for City Employees |  | 2016-12-01 | 2016-12-30 | Nick H., Bill Brecks, City Administrator, Division Heads
| Prepare and deliver 30-45 minute general presentation to include Stormwater Program overview, city programs, and how they can help. |  |  |  | Nick H., Bill Brecks |  |  |  |  | 22d
| Establish schedule for all city staff to participate in presentation (offer multiple dates/times) |  |  |  | Nick H., Bill Brecks, City Administrator, Department Heads |  |  |  |  | 22d
| BMP 3: Review Policies & Procedures for Storm Drain System Inspection & Maintenance |  | 2016-12-01 | 2016-12-30
| Document current procedures for storm drain inspection & maintenance. |  |  |  | Nick H., Bill Brecks, Facility Manager |  |  |  |  | 22d
| Draft a Catch Basin Cleanout & Disposal Standard Operating Procedure (SOP). |  |  |  | Nick H., Bill Brecks, Facility Manager |  | Saved for 2017
| Review Draft SOP with appropriate staff |  |  |  | Nick H., Bill Brecks, Facility Manager |  | Saved for 2017
| Finalize and implement catch basin cleanout & disposal SOP |  |  |  | Nick H., Bill Brecks, Facility Manager |  | Track number of catch basins inspected and cleaned out.
| BMP 4: Review Policies and Procedures for Street Sweeping to Remove Pollutants. |  | 2016-12-01 | 2016-12-30
| Document current procedures for street sweeping. |  |  |  | Nick H., Bill Brecks, Facility Manager |  | SWMP: Clean a minimum of 50% of all paved streets each year. |  |  | 22d
| Draft a Street Sweeping & Disposal Standard Operating Procedure (SOP) |  |  |  | Nick H., Bill Brecks, Facility Manager |  | Saved for 2017
| Review Draft SOP with appropriate staff |  |  |  | Nick H., Bill Brecks, Facility Manager |  | Saved for 2017
| Finalize and implement Street Sweeping & Disposal SOP. |  |  |  | Nick H., Bill Brecks, Facility Manager |  | Saved for 2017