## Sheet1
| August |  |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December
| 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
MCM 1: Public Education & Outreach
BMP 1: Develop Education Materials & Media Campaigns in Various Forms
BMP 2: Stormwater Program Website Updating | bar: August 4 to August 5
BMP 3: Cooperate with local community organizations to provide stormwater education | bar: September 1 to September 2
BMP 4: Develop Public Service Announcements | bar: August 4 to August 5
MCM 2: Public Involvement
BMP 1: Develop Call-In System for public to access educational information related to stormwater | bar: August 4 to August 5
BMP 2: Update existing City website to include information on stormwater, with links to other useful sites | bar: August 4 to August 5
BMP 3: Organize & hold public meetings and attend meetings to discuss stormwater program and solicit feedback.
BMP 4: Sponsor a community-wide cleanup Day and encourage individual and group participation. Emphasize contaminants contributing to the impairment of the Platte River. | bar: November 1 to November 4
MCM 3: Illicit Discharge Detection & Elimination (IDDE)
BMP 1: Develop Standard Operating Procedures for Program | bar: September 1 to September 4
BMP 2: Storm Sewer System mapping | bar: September 1 to December 4
BMP 3: Perform Dry Weather Inspections for Outfalls | bar: September 1 to October 5
BMP 4: Storm Drain Stenciling
BMP 5: Use PEO Materials to educate public about illegal dumping and illicit discharges. | bar: October 1 to October 5
MCM 4: Construction Stormwater Management
BMP 1: Develop an Erosion & Sediment Control Ordinance | bar: August 1 to September 4
BMP 2: Develop or Adopt Design Standards for Stormwater Runoff Control Measures
BMP 3: Site Inspection and Plan Review Program
BMP 4: Educate Contractors and the Development Community | bar: December 1 to December 4
MCM 5: Post-Construction Stormwater Management
BMP 1: Develop a Post-Construction Stormwater Ordinance | bar: October 1 to October 5
BMP 2: Develop Post-Construction Stormwater Treatment BMP Inspection and Plan Review SOP's
BMP 3: Develop Educational materials for the Development community
MCM 6: Good Housekeeping & Pollution Prevention
BMP 1: Evaluate Municipal Operations & minimuze pollutant exposure to stormwater runoff | bar: August 1 to September 4
BMP 2: General Stormwater Good Housekeeping & Pollution Prevention Training for City Employees | bar: December 1 to December 4
BMP 3: Review Policies & Procedures for Storm Drain System Inspection & Maintenance | bar: December 1 to December 4
BMP 4: Review Policies and Procedures for Street Sweeping to Remove Pollutants. | bar: December 1 to December 4
Reporting
NDEQ MS4 Stormwater Grant Funds | bar: December 1 to December 4
MS4 Permit Annual Report